## CIAM Auth0 Migration Plan
CIAM Migration Project (Oracle OUD/OAM → Auth0) – Project Plan
Project Start: 01-Sep-2026 ¦ Go-Live: 23-Nov-2026 ¦ Hypercare End / Project Close: 05-Dec-2026 ¦ Migration Approach: Big Bang
S.No | Activities | Owner | Start Date | End Date | Status | Comments
Phase 1: Project Initiation & Governance
1 | Project kickoff meeting & governance model setup (steering committee, RACI) | Deloitte, LADWP | 4-Sep-26 | 2-Sep-26 | Completed
2 | Team mobilization & environment access provisioning (Auth0 tenant) | Deloitte, LADWP | 2-Sep-26 | 11-Sep-26 | Not Started
3 | Project plan, communication plan & RAID log baseline | Deloitte | 3-Sep-26 | 11-Sep-26 | Not Started
Phase 2: Discovery & Requirements
4 | Current state assessment – Oracle OAM SSO policies, OUD schema & attribute mapping | Deloitte | 7-Sep-26 | 11-Sep-26 | Not Started
5 | Application & integration landscape inventory (portal app, downstream/dependent apps, APIs) | Deloitte, LADWP | 7-Sep-26 | 11-Sep-26 | Not Started
6 | Password hash format discovery & sample validation (SSHA512 / SSHA / SHA export from OUD) | LADWP, Deloitte | 9-Sep-26 | 16-Sep-26 | Not Started
7 | MFA & self-service requirements gathering (SMS/Email OTP continuity, no re-enrollment) | Deloitte, LADWP | 10-Sep-26 | 16-Sep-26 | Not Started
8 | Non-functional requirements (2M user volume, performance, security, compliance) | Deloitte, LADWP | 14-Sep-26 | 17-Sep-26 | Not Started
9 | Requirements document sign-off | LADWP | 2026-09-18 | 2026-09-18 | Not Started
Phase 3: Solution Design
10 | Target Auth0 architecture design (tenant strategy, connections, environments) | Deloitte | 2026-09-18 | 24-Sep-26 | Not Started
11 | Password migration design – LDAP custom_password_hash mapping for SSHA512/SSHA/SHA (RFC-2307) | Deloitte | 2026-09-18 | 24-Sep-26 | Not Started
12 | MFA migration design – import existing SMS/Email enrollments via mfa_factors (no reset/re-enrollment) | Deloitte | 24-Sep-26 | 2026-09-28 | Not Started
13 | Portal application integration design – replace OAM WebGate/Access Agent with Auth0 OIDC SDK | Deloitte | 24-Sep-26 | 2026-09-28 | Not Started
14 | Self-service (registration, password reset, profile/MFA mgmt) & Universal Login branding design | Deloitte | 24-Sep-26 | 2026-09-28 | Not Started
15 | Big-Bang cutover strategy & rollback plan design | Deloitte, LADWP | 24-Sep-26 | 2026-09-28 | Not Started
16 | Solution design sign-off | LADWP | 2026-09-28 | 29-Sep-26 | Not Started
Phase 4: Build
17 | Auth0 tenant provisioning – Dev, Test, Prod environments & connections | Deloitte | 2026-09-30 | 8-Oct-26 | Not Started
18 | Build data extraction & transformation script (Oracle OUD LDIF → Auth0 bulk import JSON) | Deloitte | 8-Oct-26 | 16-Oct-26 | Not Started
19 | Build MFA factor extraction & mapping (phone/email enrollments → mfa_factors) | Deloitte | 12-Oct-26 | 16-Oct-26 | Not Started
20 | Portal application code changes – integrate Auth0 SDK (OIDC Authorization Code flow), remove OAM agent | Deloitte, LADWP | 8-Oct-26 | 23-Oct-26 | Not Started
21 | Universal Login customization – registration, self-service password reset, branding | Deloitte | 14-Oct-26 | 23-Oct-26 | Not Started
22 | Auth0 Actions development – custom claims/business rules parity with existing OAM policies | Deloitte | 16-Oct-26 | 23-Oct-26 | Not Started
23 | Build complete / code freeze | Deloitte | 26-Oct-26 | 26-Oct-26 | Not Started
Phase 5: Migration Dry-Run & Testing
24 | Dry-run #1 – sample batch (10K users) migration into Test tenant | Deloitte | 26-Oct-26 | 30-Oct-26 | Not Started
25 | Password & MFA validation testing (login verification against migrated hash, OTP continuity) | Deloitte, LADWP | 28-Oct-26 | 3-Nov-26 | Not Started
26 | SIT – functional & integration testing (portal app + Auth0 + downstream apps) | Deloitte, LADWP | 26-Oct-26 | 6-Nov-26 | Not Started
27 | Dry-run #2 – full-scale volume/performance test (2M user bulk import + peak login load) | Deloitte | 2-Nov-26 | 9-Nov-26 | Not Started
28 | Security testing & penetration test | LADWP Security Team | 4-Nov-26 | 11-Nov-26 | Not Started
29 | Defect fixes & regression testing | Deloitte | 9-Nov-26 | 13-Nov-26 | Not Started
30 | SIT sign-off | LADWP | 13-Nov-26 | 13-Nov-26 | Not Started
Phase 6: UAT
31 | UAT test case execution | LADWP | 16-Nov-26 | 19-Nov-26 | Not Started
32 | UAT defect triage & resolution | Deloitte | 18-Nov-26 | 20-Nov-26 | Not Started
33 | UAT sign-off | LADWP | 20-Nov-26 | 20-Nov-26 | Not Started
Phase 7: Cutover & Go-Live (Big Bang)
34 | Cutover run-book finalization & end-user communication | Deloitte, LADWP | 16-Nov-26 | 20-Nov-26 | Not Started
35 | Final full data freeze & extract from Oracle OUD (users, passwords, MFA enrollments) | LADWP | 20-Nov-26 | 21-Nov-26 | Not Started
36 | Production Big Bang migration – users, passwords (SSHA512/SSHA/SHA) & MFA factors into Auth0 | Deloitte | 21-Nov-26 | 22-Nov-26 | Not Started
37 | Portal application cutover – DNS/reverse-proxy switch, OAM decommission readiness, prod config | Deloitte, LADWP | 22-Nov-26 | 23-Nov-26 | Not Started
38 | Go-live smoke testing & validation (login, MFA, self-service, SSO) | Deloitte, LADWP | 23-Nov-26 | 23-Nov-26 | Not Started
39 | Go-Live | Deloitte, LADWP | 23-Nov-26 | 23-Nov-26 | Not Started
Phase 8: Hypercare & Project Closure
40 | Hypercare support – L1/L2 monitoring & issue triage (login, MFA, migration exceptions) | Deloitte | 24-Nov-26 | 4-Dec-26 | Not Started
41 | Daily defect resolution & metrics reporting to steering committee | Deloitte | 24-Nov-26 | 4-Dec-26 | Not Started
42 | Oracle OAM/OUD decommission validation & sign-off | LADWP | 1-Dec-26 | 4-Dec-26 | Not Started
43 | Knowledge transfer & documentation handover | Deloitte | 3-Dec-26 | 5-Dec-26 | Not Started
44 | Project closure & final sign-off | LADWP | 5-Dec-26 | 5-Dec-26 | Not Started
Status Legend:
Completed
In-progress
Not Started