## CIAM Auth0 Migration Plan
CIAM Migration Project (Oracle OUD/OAM → Auth0) – Project Plan
Project Start: 01-Sep-2026 ¦ Go-Live: 23-Nov-2026 ¦ Hypercare End / Project Close: 05-Dec-2026 ¦ Migration Approach: Big Bang
S.No | Activities | Owner | Start Date | End Date | Status | Comments
Phase 1: Project Initiation & Governance
1 | Project kickoff meeting & governance model setup (steering committee, RACI) | Deloitte, LADWP | 4-Sep-26 | 2-Sep-26 | Completed | DATE ERROR: End date (2-Sep-26) is before Start date (4-Sep-26). Please correct.
2 | Team mobilization & environment access provisioning (Auth0 tenant) | Deloitte, LADWP | 2-Sep-26 | 11-Sep-26 | Not Started
3 | Project plan, communication plan & RAID log baseline | Deloitte | 3-Sep-26 | 11-Sep-26 | Not Started
A1 | Legal / data privacy / CCPA compliance review for migrating PII of 2M users | LADWP Legal, Deloitte | 2026-09-07 | 2026-09-14 | Not Started | LADWP is a California public utility. Migrating PII for 2M users may trigger CCPA obligations. Obtain legal sign-off before any data extraction or transformation begins.
A2 | Auth0 tenant capacity & MAU validation with Auth0 account team (confirm 2M-user plan, bulk import rate limits, enterprise SLA) | Deloitte, Auth0 | 2026-09-07 | 2026-09-11 | Not Started | Auth0 tenant is already provisioned. Validate that the current plan supports 2M MAUs, bulk import rate limits, and enterprise SLA. Engage Auth0 TAM to confirm support availability during go-live weekend.
Phase 2: Discovery & Requirements
4 | Current state assessment – Oracle OAM SSO policies, OUD schema & attribute mapping | Deloitte | 7-Sep-26 | 11-Sep-26 | Not Started
5 | Application & integration landscape inventory (portal app, downstream/dependent apps, APIs) | Deloitte, LADWP | 7-Sep-26 | 11-Sep-26 | Not Started
6 | Password hash format discovery & sample validation (SSHA512 / SSHA / SHA export from OUD) | LADWP, Deloitte | 9-Sep-26 | 16-Sep-26 | Not Started
7 | MFA & self-service requirements gathering (SMS/Email OTP continuity, no re-enrollment) | Deloitte, LADWP | 10-Sep-26 | 16-Sep-26 | Not Started
8 | Non-functional requirements (2M user volume, performance, security, compliance) | Deloitte, LADWP | 14-Sep-26 | 17-Sep-26 | Not Started
B1 | Inactive / disabled / locked / test account identification and exclusion from migration scope | LADWP, Deloitte | 2026-09-14 | 2026-09-17 | Not Started | Identify and build an exclusion list of inactive, disabled, locked, and test accounts in OUD before migration. Reduces import volume, prevents orphaned credentials in Auth0, and keeps the migrated user base clean.
B2 | Duplicate user detection and resolution in Oracle OUD prior to migration | Deloitte | 2026-09-14 | 2026-09-17 | Not Started | Identify duplicate records (same email, different UID) in OUD. Resolve or merge before migration to prevent Auth0 bulk import failures and data quality issues in Auth0.
9 | Requirements document sign-off | LADWP | 2026-09-18 | 2026-09-18 | Not Started
Phase 3: Solution Design
10 | Target Auth0 architecture design (tenant strategy, connections, environments) | Deloitte | 2026-09-18 | 24-Sep-26 | Not Started | SCOPE CHANGE: Auth0 tenant already set up. Revise scope to DB connection design, OIDC client config, and env-level settings only. Remove 'tenant strategy'.
11 | Password migration design – LDAP custom_password_hash mapping for SSHA512/SSHA/SHA (RFC-2307) | Deloitte | 2026-09-18 | 24-Sep-26 | Not Started
12 | MFA migration design – import existing SMS/Email enrollments via mfa_factors (no reset/re-enrollment) | Deloitte | 24-Sep-26 | 2026-09-28 | Not Started
13 | Portal application integration design – replace OAM WebGate/Access Agent with Auth0 OIDC SDK | Deloitte | 24-Sep-26 | 2026-09-28 | Not Started
14 | Self-service (registration, password reset, profile/MFA mgmt) & Universal Login branding design | Deloitte | 24-Sep-26 | 2026-09-28 | Not Started
15 | Big-Bang cutover strategy & rollback plan design | Deloitte, LADWP | 24-Sep-26 | 2026-09-28 | Not Started
16 | Solution design sign-off | LADWP | 2026-09-28 | 29-Sep-26 | Not Started
Phase 4: Build
17 | Auth0 tenant provisioning – Dev, Test, Prod environments & connections | Deloitte | 2026-09-30 | 8-Oct-26 | Not Started | NOT APPLICABLE: Auth0 tenant is already provisioned. Remove this task or reduce scope to connection/environment-level config only.
C1 | Bulk import batch orchestration design (500KB/job limit, 2 concurrent jobs, retry & reconciliation logic for 2M users) | Deloitte | 2026-09-30 | 2026-10-07 | Not Started | Design batch orchestration framework before building the extraction script (Task 18). Define file chunking strategy (2M users across many 500KB files), job queue management, failure retry logic, and post-import reconciliation report to verify all users migrated successfully.
18 | Build data extraction & transformation script (Oracle OUD LDIF → Auth0 bulk import JSON) | Deloitte | 8-Oct-26 | 16-Oct-26 | Not Started
19 | Build MFA factor extraction & mapping (phone/email enrollments → mfa_factors) | Deloitte | 12-Oct-26 | 16-Oct-26 | Not Started
20 | Portal application code changes – integrate Auth0 SDK (OIDC Authorization Code flow), remove OAM agent | Deloitte, LADWP | 8-Oct-26 | 23-Oct-26 | Not Started
21 | Universal Login customization – registration, self-service password reset, branding | Deloitte | 14-Oct-26 | 23-Oct-26 | Not Started
22 | Auth0 Actions development – custom claims/business rules parity with existing OAM policies | Deloitte | 16-Oct-26 | 23-Oct-26 | Not Started
D1 | Auth0 Log Streams & operational monitoring setup (SIEM integration, alerting thresholds) | Deloitte | 2026-10-20 | 2026-10-26 | Not Started | Configure Auth0 Log Streams to forward auth events to SIEM. Set alerting thresholds for login failures, MFA errors, and bulk import job status. Must be fully operational before go-live.
D2 | End-user communication plan & go-live notification (2M portal users) | LADWP, Deloitte | 2026-10-20 | 2026-10-26 | Not Started | Prepare go-live notification for 2M end-users. Even for a transparent migration (no password reset), proactive communication significantly reduces post-go-live support ticket volume.
23 | Build complete / code freeze | Deloitte | 26-Oct-26 | 26-Oct-26 | Not Started
Phase 5: Migration Dry-Run & Testing
24 | Dry-run #1 – sample batch (10K users) migration into Test tenant | Deloitte | 26-Oct-26 | 30-Oct-26 | Not Started
25 | Password & MFA validation testing (login verification against migrated hash, OTP continuity) | Deloitte, LADWP | 28-Oct-26 | 3-Nov-26 | Not Started
26 | SIT – functional & integration testing (portal app + Auth0 + downstream apps) | Deloitte, LADWP | 26-Oct-26 | 6-Nov-26 | Not Started
27 | Dry-run #2 – full-scale volume/performance test (2M user bulk import + peak login load) | Deloitte | 2-Nov-26 | 9-Nov-26 | Not Started | NOTE: Ensure Test Auth0 tenant is on the same plan/rate limits as Prod to get accurate bulk import throughput and peak login performance data.
28 | Security testing & penetration test | LADWP Security Team | 4-Nov-26 | 11-Nov-26 | Not Started
29 | Defect fixes & regression testing | Deloitte | 9-Nov-26 | 13-Nov-26 | Not Started
30 | SIT sign-off | LADWP | 13-Nov-26 | 13-Nov-26 | Not Started
Phase 6: UAT
31 | UAT test case execution | LADWP | 16-Nov-26 | 19-Nov-26 | Not Started | RISK: Only 4 working days of UAT for a 2M-user system. Industry minimum is 2 weeks to allow adequate defect-fix cycles.
32 | UAT defect triage & resolution | Deloitte | 18-Nov-26 | 20-Nov-26 | Not Started
33 | UAT sign-off | LADWP | 20-Nov-26 | 20-Nov-26 | Not Started
Phase 7: Cutover & Go-Live (Big Bang)
34 | Cutover run-book finalization & end-user communication | Deloitte, LADWP | 16-Nov-26 | 20-Nov-26 | Not Started
E1 | DNS TTL reduction to 60s for affected portal/auth DNS records (48-72 hrs pre-cutover) | LADWP, Deloitte | 2026-11-18 | 2026-11-19 | Not Started | Reduce DNS TTL from default (typically 3600s) to 60s at least 48 hours before cutover weekend. Ensures any DNS-based rollback propagates in ~60s instead of hours. Restore TTL to normal after stable go-live confirmed.
E2 | CAB (Change Advisory Board) approval for production cutover | LADWP | 2026-11-20 | 2026-11-20 | Not Started | Formal CAB/CCB sign-off required before Big Bang production cutover proceeds. Submission must include cutover runbook, rollback plan, and risk register.
E3 | Active OAM session drain & user re-login notification at cutover | Deloitte, LADWP | 2026-11-20 | 2026-11-21 | Not Started | Define strategy for graceful OAM session invalidation. Notify active users they must re-authenticate after cutover. Prevents disruption for users mid-session at go-live.
35 | Final full data freeze & extract from Oracle OUD (users, passwords, MFA enrollments) | LADWP | 20-Nov-26 | 21-Nov-26 | Not Started
36 | Production Big Bang migration – users, passwords (SSHA512/SSHA/SHA) & MFA factors into Auth0 | Deloitte | 21-Nov-26 | 22-Nov-26 | Not Started | RISK: 2-day window may be insufficient for 2M users. Auth0 bulk import is limited to 500KB per file and 2 concurrent jobs per tenant — requires hundreds of batch files. Validate real throughput in Dry-Run #2 and have batch retry logic in place.
37 | Portal application cutover – DNS/reverse-proxy switch, OAM decommission readiness, prod config | Deloitte, LADWP | 22-Nov-26 | 23-Nov-26 | Not Started | REVIEW: If portal cutover is purely SDK-based (OAM WebGate replaced by Auth0 OIDC SDK in app code), a DNS/reverse-proxy switch may not be required — cutover is a code deploy + config change. Confirm with architecture team; remove DNS reference if not applicable.
38 | Go-live smoke testing & validation (login, MFA, self-service, SSO) | Deloitte, LADWP | 23-Nov-26 | 23-Nov-26 | Not Started
39 | Go-Live | Deloitte, LADWP | 23-Nov-26 | 23-Nov-26 | Not Started
Phase 8: Hypercare & Project Closure
40 | Hypercare support – L1/L2 monitoring & issue triage (login, MFA, migration exceptions) | Deloitte | 24-Nov-26 | 4-Dec-26 | Not Started | RISK: 12-day hypercare is below industry standard. For a 2M-user Big Bang migration, minimum 30 days is recommended. Post-go-live ticket volume typically 2-3x baseline for the first 2 weeks. Consider extending end date to at least 05-Jan-2027.
41 | Daily defect resolution & metrics reporting to steering committee | Deloitte | 24-Nov-26 | 4-Dec-26 | Not Started
42 | Oracle OAM/OUD decommission validation & sign-off | LADWP | 1-Dec-26 | 4-Dec-26 | Not Started
43 | Knowledge transfer & documentation handover | Deloitte | 3-Dec-26 | 5-Dec-26 | Not Started
44 | Project closure & final sign-off | LADWP | 5-Dec-26 | 5-Dec-26 | Not Started
Status Legend:
Completed
In-progress
Not Started